## Deliverable Tracker
UNCLE ROBERT CONSULTING LLC ¦ Deliverable Tracker
Fulfillment Department ¦ Workflow 1: Display & Packaging ¦ Updated: March 12, 2026
Client ID | Client Name | Project/Milestone | Deliverable Type | Format | Complexity | Template Applied? | Brand Config Done? | Content Integrated? | Packaged? | Agreed Delivery Date | Actual Delivery Date | Tracking Link Sent? | Client Opened? | First-Pass Approved? | Brand Compliance | Days Early/Late | Overall Status
URC-001 | RealEdge LLC | AI Playbook - Month 1 | Playbook | PDF | High | Yes | Yes | Yes | Yes | 2026-03-15 | 2026-03-14 | Yes | Yes | Yes | Pass | -1 | Approved
URC-002 | BlueSky Corp | Automation Setup Report | Report | Google Doc | Medium | Yes | Yes | Yes | Yes | 2026-03-18 |  | Yes | No |  | Pending | 0 | Delivered
URC-003 | Nova Health | Workflow Dashboard | Dashboard | Google Slides | High | Yes | Yes | Pending | No | 2026-03-22 |  | No |  |  | Pending | 0 | In Review
URC-004 | Apex Digital | Strategy Doc Q1 | Strategy Doc | PDF | Medium | Yes | Yes | Yes | Yes | 2026-03-20 | 2026-03-21 | Yes | Yes | Yes | Pass | 1 | Approved
URC-005 | Bloom & Co | Training Materials Set | Training Material | PDF | Complex | Yes | Pending | No | No | 2026-03-28 |  | No |  |  | Pending | 0 | In Progress
URC-006 | Crest Capital | Onboarding Package | Playbook | Canva | Medium | Yes | Yes | Yes | Yes | 2026-03-12 | 2026-03-12 | Yes | Yes | Yes | Pass | 0 | Approved
URC-007 | Spark Studios | Content Strategy Report | Report | PDF | Low | Yes | Yes | Yes | Yes | 2026-03-10 | 2026-03-10 | Yes | Yes | No | Revision |  | Revision Needed
URC-008 | TechVault | Monthly KPI Dashboard | Dashboard | Google Slides | Medium | Yes | Yes | Yes | Yes | 2026-03-08 | 2026-03-07 | Yes | Yes | Yes | Pass | -1 | Approved
URC-009 | Greenpath Co | Automation Audit | Report | PDF | Medium | Yes | Yes | Yes | No | 2026-03-25 |  | No |  |  | Pending | 0 | Packaged
URC-010 | Nexus Media | Digital Product Launch Kit | Digital Product | Canva | Complex | No | No | No | No | 2026-04-01 |  | No |  |  | Pending | 0 | Not Started
URC-011 | Holmes Media | Stranger Things Fingerprint Hunt | Playbook | PDF | Medium | No | Yes | Yes | No | 2026-03-31 | 2026-03-15 | No | No | No | Pending |  | In Progress
URC-012 | Five Aces | Short Term Action Plan | Strategy Doc | Word | Medium | No | Yes | Yes | No | 2026-03-31 |  | No | No | No | Pending |  | In Review
URC-013 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-014 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-015 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-016 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-017 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-018 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-019 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-020 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-021 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-022 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-023 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-024 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started
URC-025 |  |  | Report | PDF | Medium | No | No | No | No |  |  | No | No | No | Pending |  | Not Started