## Strategic Plan
UNCLE ROBERT CONSULTING LLC — Strategy & Planning Dashboard (CUL-07)
Annual Strategic Plan ¦ Quarterly Milestones ¦ Financial Targets ¦ AI Roadmap
2026 ANNUAL STRATEGIC PILLARS
Pillar # | Strategic Pillar | Description | Primary Owner | Q1 Focus | Q2 Focus | Annual Target
P1 | AI-Native Service Expansion | Launch 2+ new AI-native consulting products for creator economy | Robert | Research & define services | Beta launch with 5 clients | 2 new services launched, 15+ clients
P2 | Operational Efficiency | Automate 60%+ of agency operations using AI and Zapier | Robert + Jerome | Complete 30-SOP library | Build 5 core automations | 60% automation rate achieved
P3 | Client Retention & Community | Achieve 90%+ retention and launch Circle community with 50+ members | Marcus | Identify at-risk clients | Launch community platform | 90%+ retention, 50+ members
P4 | Team Capability Growth | Build all 4 AMs to Level 3+ competency across core skills | Robert | Baseline assessments done | All HubSpot certs completed | Avg competency score 3.5+

## Quarterly Sprints
Quarterly Sprint Milestones — 90-Day Planning
Quarter | Milestone | Strategic Pillar | Owner | Target Date | Status | Completion % | Notes
Q1 2026 | Complete SOP library — 30+ active SOPs | P2 | Keisha | 2026-03-31 | In Progress | 55 | 16 of 30 target SOPs active
Q1 2026 | Baseline team competency assessment | P4 | Robert | 2026-03-31 | Completed | 100 | Scores logged in CUL-05
Q1 2026 | HubSpot certification — Marcus | P4 | Marcus | 2026-03-31 | Completed | 100 | Passed Feb 5
Q1 2026 | Build first 3 Zapier automations | P2 | Jerome | 2026-03-31 | In Progress | 66 | Lead intake and reporting done; follow-up in progress
Q1 2026 | Define 2 new AI-native service offerings | P1 | Robert | 2026-03-31 | In Progress | 40 | Service 1 defined; Service 2 in draft
Q2 2026 | Beta launch 2 AI-native services with 5 clients each | P1 | Robert + Marcus | 2026-06-30 | Not Started | 0
Q2 2026 | Launch Circle community platform with 50+ members | P3 | Marcus | 2026-06-30 | Not Started | 0
Q2 2026 | All 4 AMs complete HubSpot certification | P4 | All AMs | 2026-06-30 | In Progress | 25 | Marcus done; 3 remaining
Q2 2026 | Achieve 60%+ AI automation rate | P2 | Jerome | 2026-06-30 | Not Started | 0
Q2 2026 | Collect 10 client video testimonials | P3 | Destiny | 2026-06-30 | Not Started | 0

## Financial Model
URC Financial Plan 2026 — Monthly Budget vs. Actuals
Metric | Monthly Budget | Monthly Actual | Variance ($) | Variance (%)
REVENUE
Business Coaching Revenue | 5000
Consulting Revenue | 3000
Monetization Optimization Revenue | 2000
Course / Product Revenue | 1500
Retainer / Subscription Revenue | 8500
TOTAL REVENUE | 20000
OPERATING COSTS
Team / Contractor Costs | 6000
SaaS Tool Subscriptions | 2500
Marketing & Advertising | 1000
Professional Development | 500
Office / Operations | 300
TOTAL COSTS | 10300
NET MARGIN | 9700
MARGIN % | 48.5%

## AI Roadmap
URC AI-Native Agency Roadmap — Workflow to Playbook to Agent
Phase | Milestone | Department | Owner | Target Date | Status
Phase 1: Foundations | All 4 department workflow docs complete | All | Robert | 2026-03-31 | Completed
Phase 1: Foundations | 30+ SOPs in active repository | Culture | Keisha | 2026-03-31 | In Progress
Phase 1: Foundations | Tech stack rationalized — remove redundancies | Culture | Robert | 2026-04-30 | Not Started
Phase 1: Foundations | All team members on required tools with RBAC | Culture | Robert | 2026-04-30 | In Progress
Phase 2: AI-Native Delivery | First 3 Zapier automations live (lead, report, follow-up) | Sales/Ops | Jerome | 2026-05-31 | In Progress
Phase 2: AI-Native Delivery | AI Discovery Summarizer agent deployed in HubSpot | Sales | Robert | 2026-05-31 | Not Started
Phase 2: AI-Native Delivery | AI Content Sequencer agent deployed in ClickUp | Fulfillment | Marcus | 2026-06-30 | Not Started
Phase 2: AI-Native Delivery | AI Reporting Agent generating weekly dashboards | Culture | Jerome | 2026-06-30 | Not Started
Phase 2: AI-Native Delivery | 60%+ agency automation rate achieved | All | Robert | 2026-06-30 | Not Started
Phase 3: Productization | First AI-native productized service launched | Sales | Robert | 2026-09-30 | Not Started
Phase 3: Productization | First white-label workflow template sold | Sales | Robert | 2026-09-30 | Not Started
Phase 3: Productization | Agency positioned as fractional AI-native partner | Marketing | Robert | 2026-12-31 | Not Started