## Quality Issue Log
UNCLE ROBERT CONSULTING LLC ¦ Quality Issue Log
Operations Department ¦ OPS-08: R&D & Quality Assurance ¦ Updated: March 18, 2026
Issue ID | Date Identified | Department | Process / Workflow | Issue Description | Severity | Root Cause | Assigned To | Resolution Action | Resolved Date | SOP Updated? | Status
QA-001 | 2026-01-08 | Fulfillment | Client Deliverable QA | Deliverable sent to client without final brand compliance check | Medium | Step skipped in rush | R. McCarthy | Added mandatory QA checklist step to FUL-01 SOP | 2026-01-10 | Yes | Resolved
QA-002 | 2026-01-22 | Finance | Invoice Generation | Invoice sent with incorrect service description | Low | Manual copy error | R. McCarthy | Built invoice auto-population from HubSpot deal fields | 2026-01-25 | Yes | Resolved
QA-003 | 2026-02-05 | Marketing | Lead Capture | Make.com webhook failed silently — 3 leads lost | High | No error alerting configured | R. McCarthy | Added Slack error alert to all Make.com workflows | 2026-02-06 | Yes | Resolved
QA-004 | 2026-02-18 | Sales | Proposal Delivery | Proposal sent before rep reviewed AI draft | Medium | Auto-send triggered too early | R. McCarthy | Added 24hr draft-only hold to proposal workflow | 2026-02-20 | Yes | Resolved
QA-005 | 2026-03-02 | Fulfillment | Client Check-In | Missed 30-day check-in for one client | Medium | No automated reminder set | R. McCarthy | Configured automated 30-day check-in task in ClickUp | 2026-03-03 | Yes | Resolved
QA-006 | 2026-03-10 | Operations | Tech Stack | 1Password shared vault had stale credentials for exited contractor | High | No offboarding checklist | R. McCarthy | Built offboarding checklist; audited all shared credentials | 2026-03-12 | Yes | Resolved
QA-007 | 2026-03-15 | Marketing | Content Publish | Blog post published without SEO meta description | Low | Step missing from content SOP | R. McCarthy | Added SEO checklist to MKT-03 SOP | 2026-03-16 | Yes | Resolved
QA-008 | 2026-03-17 | Sales | Onboarding | Client intake form submitted incomplete — missing brand assets | Medium | No required-field enforcement | R. McCarthy | Set intake form fields to required; added 48hr follow-up reminder |  | No | In Progress
QA-009 | 2026-03-18 | Finance | Expense Tracking | Two subscriptions charged to personal card instead of business | Low | Billing method not updated | R. McCarthy | Auditing all vendor billing; updating to business card |  | No | In Progress
QA-010 | 2026-03-18 | Operations | SOP Repository | 3 SOPs missing next review dates | Low | Template gap | R. McCarthy | Updating SOP template to require review date field |  | No | In Progress