## Onboarding Tracker
UNCLE ROBERT CONSULTING LLC ¦ Client Onboarding Checklist Tracker 1
Sales Department ¦ OnBoarding Workflow ¦ Updated: March 11, 2026
Client ID | Client Name | Welcome Email Sent? | Portal Access Given? | Welcome Video Sent? | Intake Form Sent? | Intake Completed? | Assets Received? | Internal Brief Done? | Project Created? | Team Assigned? | Kickoff Scheduled? | Kickoff Date | Kickoff Completed? | First Deliverable Date | Client Reviewed? | 30-Day Survey Sent? | Overall Status
OB-001 | RealEdge LLC | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2026-03-15 | Yes | 2026-03-22 | Pending | No | In Progress
OB-002 | BlueSky Corp | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2026-03-14 | No |  | No | No | In Progress
OB-003 | Nova Health | Yes | Yes | No | Yes | Yes | Partial | No | No | No | No |  | No |  | No | No | At Risk
OB-004 | Apex Digital | Yes | No | No | Yes | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-005 | Bloom & Co | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No |  | No |  | No | No | On Track
OB-006 | TechVault | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2026-03-10 | Yes | 2026-03-17 | Yes | Yes | Complete
OB-007 | Spark Studios | Yes | Yes | No | Yes | Pending | No | No | No | No | No |  | No |  | No | No | At Risk
OB-008 | Nexus Media | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2026-03-12 | Yes | 2026-03-19 | Pending | No | On Track
OB-009 | Crest Capital | Yes | No | No | Yes | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-010 | Greenpath Co | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2026-03-08 | Yes | 2026-03-15 | Yes | Yes | Complete
OB-011 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-012 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-013 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-014 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-015 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-016 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-017 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-018 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-019 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-020 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-021 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-022 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-023 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-024 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started
OB-025 |  | No | No | No | No | No | No | No | No | No | No |  | No |  | No | No | Not Started