## Onboarding (Detailed)
UNCLE ROBERT CONSULTING LLC ¦ Client Onboarding Checklist Tracker 2 – Health Score Edition
Sales Department ¦ OnBoarding Workflow ¦ Updated: March 11, 2026
Client ID | Client Name | Account Manager | Welcome Email Sent? | Portal Access? | Welcome Video? | Onboarding Timeline Shared? | Intake Form Sent? | Intake Completed? | Assets Received? | Intake Completion % | Internal Brief? | Project Created? | Kickoff Date | Kickoff Completed? | First Deliverable Date | Client Review Status | Revisions Required | Final Approval? | 30-Day Survey Sent? | Satisfaction Score (1-10) | Churn Risk | Health Score (1-100) | Overall Status
OB-001 | RealEdge LLC | Jerome | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 100% | Yes | Yes | 2026-03-15 | Yes | 2026-03-22 | In Review | Minor | Pending | No | 8 | Low | 82 | On Track
OB-002 | BlueSky Corp | Keisha | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 90% | Yes | Yes | 2026-03-14 | Yes | 2026-03-21 | Pending | 0 | No | No |  | Low | 78 | In Progress
OB-003 | Nova Health | Jerome | Yes | Yes | No | Yes | Yes | Yes | Partial | 60% | No | No |  | No |  | Not Started | 0 | No | No |  | High | 42 | At Risk
OB-004 | Apex Digital | Robert | Yes | No | No | No | Yes | No | No | 10% | No | No |  | No |  | Not Started | 0 | No | No |  | Critical | 15 | At Risk
OB-005 | Bloom & Co | Marcus | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 100% | Yes | Yes | 2026-03-16 | No | 2026-03-23 | Not Started | 0 | No | No |  | Low | 70 | On Track
OB-006 | TechVault | Destiny | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 100% | Yes | Yes | 2026-03-10 | Yes | 2026-03-17 | Approved | 0 | Yes | Yes | 9 | Low | 95 | Complete
OB-007 | Spark Studios | Marcus | Yes | Yes | No | Yes | Yes | Pending | No | 30% | No | No |  | No |  | Not Started | 0 | No | No |  | High | 28 | At Risk
OB-008 | Nexus Media | Robert | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 100% | Yes | Yes | 2026-03-12 | Yes | 2026-03-19 | In Review | Major | Pending | No | 6 | Medium | 65 | On Track
OB-009 | Crest Capital | Keisha | Yes | No | No | No | Yes | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Critical | 10 | Not Started
OB-010 | Greenpath Co | Jerome | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 100% | Yes | Yes | 2026-03-08 | Yes | 2026-03-15 | Approved | 0 | Yes | Yes | 10 | Low | 98 | Complete
OB-011 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-012 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-013 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-014 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-015 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-016 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-017 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-018 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-019 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-020 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-021 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-022 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-023 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-024 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started
OB-025 |  | Robert | No | No | No | No | No | No | No | 0% | No | No |  | No |  | Not Started | 0 | No | No |  | Low | 50 | Not Started